E3 Consulting

DRAFT |  22-Dec-25

ENVIRONMENTAL AND SOCIAL ACTION PLAN (ESAP)

PROJECT: GVOZD 2 WIND FARM

GVOZD 2 WIND FARM PROJECT – MONTENEGRO

ENVIRONMENTAL AND SOCIAL ACTION PLAN (ESAP)

| No. | Action | Environmental and Social Risks | Requirement | Resources, Investment needs, Responsibilities | Timeframe | Target and Evaluation Criteria for Successful Implementation | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PR1 | Assessment and Management of Environmental and Social Impacts and Issues |  |  |  |  |  |  |
| 1.1 | Implement project-specific E&S Policy on company level, and present it to all contractors through implementation of statements on principles and values adopted in engaging with workers, subcontractors, and communities on labour, and human rights. | Promoting ESHS culture on project level and ensuring compliance with international best practices. | EBRD PR1 | EPCG/Green Gvozd to implement on project level, and to introduce as an obligation to all contractors OESC to monitor implementation during the construction phase EPCG/Green Gvozd to monitor implementation during the operation phase | Q1/2026 for Gvozd 1 and prior to commencement of implementation for Gvozd 2 | Project-level E&S Policy implemented and introduced to all contractors (both for Gvozd 1 and for Gvozd 2) |  |
| 1.2 | Each Contractor to develop C-ESMP, in accordance with this ESAP, OESC’s ESMP, Project EIA, and other project E&S documentation. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing C-ESMPs and other relevant sub-plans, if an update is necessary. | Ensure that environmental and social management measures prescribed within the EIA and SIA are implemented | EBRD PR1 | Contractors to develop and implement C-ESMPs OESC to monitor development and implementation during the construction phase | At least 1 month prior to commencement of implementation of Gvozd 2 | C-ESMP developed and implemented by all contractors |  |
| 1.3 | EPCG/Green Gvozd to develop O-ESMP which is going to include activities for managing all environmental and social risks identified in the project EIA, E&S study, ESAP, OESC’s ESMP | Ensure duly management of all environmental and social risks during the operation phase, in accordance with the official E&S impact assessments which have been developed for the Project. | EBRD PR1 | EPCG/Green Gvozd | At least 1 month prior to commencement of operation phase | O-ESMP developed and implemented by the Client. Regular reports on implementation of O-ESMP submitted to the Lender for the purpose of project performance review and monitoring. |  |
| 1.4 | EPCG/Green Gvozd to conduct weekly site inspections through OESC. Assess environmental, social and OHS performance on site. Report on performance to Lenders every three months during construction. Report frequency to be increased in the event of significant issues/incidents on site. | Ensure contractors’ adoption of international requirements for OHS | EBRD PR1 | OESC to conduct site visits EPCG/Green Gvozd to report to EBRD in cooperation with OESC | Throughout construction | Report available and submitted to Lenders quarterly |  |
| PR2 | Labour and Working Conditions |  |  |  |  |  |  |
| 2.1 | Implement Environmental and Social Management Plan (ESMP) Manual commensurate with the environmental and social risks identified through E&S assessment. | Promoting ESHS culture on project level and ensuring compliance with international best practices. | EBRD PR1 | EPCG/Green Gvozd in cooperation with OESC | Q1/2026 for Gvozd 1 and at least 1 month prior to commencement of implementation of Gvozd 2 | ESMP Manual developed, implemented and communicated to all contractors (both for Gvozd 1 and for Gvozd 2) |  |
| 2.2 | Develop and implement a Project HR Management System, including an HR Policy Statement and associated procedures. HR Policy Statement and procedures must be compliant with EBRD E&S Policy, as well as with EBRD PR2 provisions. Project HR Management System shall include the contractors’ and suppliers’ performance assessment in relation to labour and working conditions | Management of worker relationships and reduction of labour risks | EBRD PR2 International Best Practice International Labor Organization (ILO) requirements | EPCG/Green Gvozd in cooperation with OESC | Q1/2026 for Gvozd 1 and prior to commencement of implementation of Gvozd 2 | HR Policy made available to all project employees, contractors, sub-contractors and their workers |  |
| 2.3 | EPCG-Green Gvozd to appoint Project HR Manager who is going to be in charge of implementation and monitoring of HR Management System by the contractors | Project HR management on all levels, including prevention of potential labour-related issues among the contractors | EBRD PR2 International Best Practice International Labor Organization (ILO) requirements | EPCG/Green Gvozd in cooperation with OESC during the construction phase. EPCG/Green Gvozd HR Manager to continue managing project team during the operation phase | Q1/2026 for Gvozd 1 and prior to commencement of implementation of Gvozd 2 | Project HR Manager appointed by 10th February 2025 and included in the project. HR Officer in place to implement HR Management System and Labour related aspects. |  |
| 2.4 | Contractors to develop and implement a Workers Grievance Mechanism (WGM) compliant with the applicable Project standards and covering all contractor and subcontractor workers regardless of the tier. Communicate to all workers about the processes and procedures regarding the internal grievance mechanism, ensuring that it is clear to all. The contractors will disseminate information about its use to the workforce (in a language the workers understand). The contractors will appoint or nominate a grievance/ HR officer to coordinate the implementation of the WGM. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing C-ESMPs and other relevant sub-plans, if an update is necessary. | Management of worker relationships and reduction of labour risks | EBRD PR2 International Best Practice International Labor Organization (ILO) requirements | Contractors supervised by OESC | Q1/2026 for Gvozd 1 and prior to commencement of implementation of Gvozd 2 | WGM implemented and communicated to all workers. |  |
| 2.5 | Integrate and maintain mitigation measures relating to labour and working conditions identified in this ESAP, EIA and OESC’s ESMP into the C- ESMP | Prevent employee or contractor disputes from grievances | EBRD PR2 | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | C-ESMP, including labour and working conditions provisions, developed and implemented |  |
| 2.6 | EPCG/Green Gvozd will develop and implement contractual clauses related to prohibition of forced labour, child labour and supply chain into the contracts with their vendors/suppliers. Specifically, these clauses must be included in contracts for purchase of WTG components. | Managing human rights risks, such as forced/child labour, managing reputational risks | EBRD PR2 | EPCG/Green Gvozd | Prior to delivery of WTG components | Vendors/suppliers of WTG components approved by EPCG/Green Gvozd in accordance with prior assessment of their compliance with the defined code of ethics. |  |
| PR3 | Resource Efficiency and Pollution Prevention and Control |  |  |  |  |  |  |
| 3.1 | EPCG/Green Gvozd to develop Stormwater and Erosion Management Plan for the operation phase of the Project (including the area of Gvozd 1 and Gvozd 2 platforms and access roads). The plan should platform stability monitoring (e.g. annual monitoring). | Managing potential future risks caused by climate change, weather conditions, use of the access roads | EBRD PR3 | EPCG/Green Gvozd | At least 1 month prior to commencement of operation of the entire WF and all its accompanying infrastructure (Gvozd 1 and Gvozd 2) | Stormwater and Erosion Management Plan developed and implemented throughout the entire lifecycle of operation of the WF |  |
| PR4 | Health and Safety |  |  |  |  |  |  |
| 4.1 | Contractors to develop and implement an OHS plan(s) to guide all activities on project site during site preparation, construction, and operation and ensure that all contractors adopt these plans. The OHS Plans need to be aligned with OESC’s Overall Occupational Health and Safety Plan, and this ESAP. Requirements to include, at a minimum: - Job and task-specific hazard analysis and controls for all activities - Provision of personal protection equipment (PPE), requirements for use of PPE, and enforcement of PPE use - Safety training for all personnel in their language, covering hazards and safety protocols of their jobs - Special training for specific hazards: working at heights, in excavations, with electricity - Review and approval of contractors’ OHS plans - Oversight of contractor OHS implementation, including mandatory reporting - Recording incident statistics, including total work hours, lost time incidents, major injuries, fatalities, etc. - Each contractor shall have an appointed certified OHS expert, or an expert OHS company for the duration of the project - Obtain from the Contractors hard evidence that they engaged and maintain health and safety officers with sufficient skills and that all the workers involved in potentially hazardous work are properly trained and briefed specifically for each type or work and location. - Special OHS measures to be developed for the following construction works: use of scaffolding; crane operations and prefabricated assembly; generator operation; tying, guiding loads and giving signals; operation and safe work with cranes; operation and safe work with forklifts; assembly and installation works; transport operations; work at heights; use of ladders; concreting; working on OHL power lines; working on cable lines; installing electrical power cables; working in extreme working conditions; manual handling and carrying of loads; Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing OHS Plans and other relevant sub-plans, if an update is necessary. | Duly implementation of national and international OHS commitments and prevention of any work-related incidents | EBRD PR4 | Contractors supervised by OESC and EPCG/Green Gvozd | Q1 /2026 update of OHS Plans for Gvozd 1 (where necessary), and at least 1 month prior to commencement of implementation of Gvozd 2 | OHS plans available, distributed to all contractors/sub-contractors/workers/ project employees |  |
| 4.2 | Require that Contractors implement provisions defined in the Project HR Management System, in relation to prevention of Gender-based violence and harassment (GBVH). Contractors to include provisions related to prevention of GBVH in their respective C-ESMPs. Contractors must ensure compliance with the EPCG’s E&S Policy, Project HR Management System, this ESAP, OESC’s ESMP, and other relevant E&S project commitments. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing C-ESMPs and other relevant sub-plans, if an update is necessary. | Reputational benefit and prevent damage and complaints | EBRD PR4 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | GBVH prevention provisions available in Contractors’ C-ESMPs |  |
| 4.3 | Develop a Community Health and Safety (CHS) Management Plan based on the identified risks and impacts and define mitigation measures. Plan to consider at a minimum security, exposure to diseases, influx of workers, emission of dust and particulate, emission of matter, gaseous pollutants, increase of traffic, and emission of noise and vibrations. Contractors must ensure compliance with the EPCG’s E&S Policy, Project HR Management System, this ESAP, OESC’s ESMP, and other relevant E&S project commitments. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing Community Health and Safety Plans and other relevant sub-plans, if an update is necessary. | Prevention of CHS risks and incidents, as well as community complaints | EBRD PR4 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | Community Health and Safety (CHS) Management Plan developed and implemented by all Contractors. Continuous communication with the local communities and duly management of Project Grievance Mechanism. |  |
| 4.4 | Contractors to develop Traffic Management Plan(s) (TMP) for the use of local roads for the purpose of Project traffic which ensures that local residents take priority and risks and nuisance is minimised. TMP to consider delivery of equipment and material from the port to the site, access, routing, diversions, exceptional loads, and driver training. Consult with local stakeholders and provide timely information to users of land of times access to their land may be necessary, or limited. Plans must cover transport of turbines, rock/stone, and other materials to be brought to or removed from the site. Communicate the plan to the local communities through stakeholder engagement. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing TMPs and other relevant sub-plans, if an update is necessary. | Prevention of unannounced traffic disturbance (regional and local), as well as prevention of disturbance of local population, accidents and fatalities (local communities, project workers | EBRD PR4 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | TMP developed and implemented by all contractors. TMP communicated to the local community through stakeholder engagement. |  |
| 4.5 | Contractors to develop site-specific Emergency Preparedness and Response Plan (EPRP). Plan to identify all possible emergency situations and identify mitigation and monitoring measures for such situations and communicating it to the stakeholders. Near-miss and accidents monitoring and reporting mechanism developed as part of EPRP. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing EPRPs and other relevant sub-plans, if an update is necessary. | Prevent injuries and fatalities related to Project activities, Company reputation | EBRD PR4 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | EPRP developed and implemented by all contractors. |  |
| 4.6 | Identify and implement appropriate prevention plan/mitigation measures to manage exposure of hazardous materials and ensure that they safely handled, stored, transported and disposed. This activity shall be implemented through development of Waste Management Plans (including hazardous and non-hazardous waste), which are to be developed and approved in accordance with the national legislative framework. | Prevent spillage and contamination | EBRD PR4 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of implementation of Gvozd 2 | EPRP developed and implemented by all contractors. |  |
| PR5 | Land Acquisition, Involuntary Resettlement and Economic Displacement |  |  |  |  |  |  |
| 5.1 | Contractors to cooperate with EPCG prior to accessing private land plots for the purpose of project implementation, including the land plots necessary for construction of Gvozd 2, as well as for construction of OHL. Special attention to be paid to land plots which are used for accessing the construction site (e.g. WF platforms and OHL towers locations), so as to obtain approval from land owners for using their land for accessing the work areas, and to inform them about any potential damage that may be caused to their land due to movement of mechanisation. Any damage incurred on land plots which are going to be used for accessing the work areas (both for Gvozd 2 WF and OHL line) is to be repaired by reinstating the land to pre-project condition. EPCG/Green Gvozd to provide written information about any damage incurred to the access land plots, accompanied by written statements on reinstatement of the land to the pre-project condition. | Prevent disruption of additional private land plots and complaints from the local population | EBRD PR5 International Best Practice | EPCG/Green Gvozd in cooperation with contractors | Throughout project implementation, including the OHL works | All landowners whose land is going to be used for accessing the work areas to be duly informed prior to accessing their land. Obtain written approval for access to land prior to entry to private properties, at all work positions – especially when accessing land plots which have been acquired for the purpose of construction of OHL towers (Contractor in cooperation with EPCG). Written statements provided by EPCG/Green Gvozd to landowners regarding reinstatement of their land to pre-project condition. Any grievances related to land use/damage to be duly logged and resolved by OESC Conflict Resolution Manager and EPCG/Green Gvozd CLO. |  |
| PR6 | Biodiversity and Living Natural Resources |  |  |  |  |  |  |
| PR8 | Cultural Heritage |  |  |  |  |  |  |
| 8.1 | Contractors engaged in earthworks to develop and implement Chance Find Procedure. Note: in case of engagement of the same contractors which were included in implementation of Gvozd 1, this activity shall be implemented through update of the existing Chance Find Procedures and other relevant sub-plans, if an update is necessary. | Avoid potential impact on cultural heritage and any potential chance finds during earthworks. | EBRD PR8 International Best Practice | Contractors supervised by OESC and EPCG/Green Gvozd | At least 1 month prior to commencement of works | Chance Find Procedure developed and implemented by all contractors engaged in earthworks |  |
| PR10 | Information Disclosure and Stakeholder Engagement |  |  |  |  |  |  |
| 10.1 | Provide public with relevant Project documentation by publishing documents to the Green Gvozd 2 website, to include at least the SEP and NTS of the Project; place construction notice boards at each end of the Project section, including all the nationally required Project information. | Ensure transparency on E&S issues. Reputational benefits and engagement with key stakeholders | EBRD PR10 | Company | Q1/2026 | Lender-approved Project E&S documentation officially disclosed at the Project website |  |
| 10.2 | EPCG to appoint a Community Liaison Officer (CLO) who is going to be in charge of updating this SEP, managing Grievance Mechanism, and conducting Stakeholder Engagement activities. The CLO is going to work in cooperation with the OESC’s Conflict Resolution Manager during the construction phase. During the operation phase, the CLO is going to be in charge of this SEP, stakeholder engagement and grievance management independently. | Ensure transparency on E&S issues. Reputational benefits and engagement with key stakeholders | EBRD PR10 | OESC in cooperation with EPCG/Green Gvozd during construction phase / EPCG/Green Gvozd during operation phase | Q1/2026 for Gvozd 1 and throughout construction and operation phase of Gvozd 2 | EPCG CLO appointed by 10th February 2026 and included in project activities |  |

Contractors are obliged to ensure that their sub-contractors fully comply with all the provisions and committments defined in all project-related plans and sub-plans.